## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Maddineni Kinshuk | 2025-10-04 | AI model incorrectly classified genuine Aadhaar as fake. | Sprint 1 | Maddineni Kinshuk | Functional | Improved dataset and retrained model | 2025-10-08 | Closed | Accuracy improved by 36%
2 | Maddineni Kinshuk | 2025-10-15 | Dashboard UI not displaying verification results | Sprint 2 | Maddineni Kinshuk | UI/UX | Fixed Frontend | 2025-10-21 | Closed | Verified in testing
3 | Maddineni Kinshuk | 2025-10-21 | Unable to decode the aadhaar qr code. | Sprint 3 | Maddineni Kinshuk | Functional | Implemented developed modules | 2025-10-26 | Open | Not authorised to decode qr code

## Sheet2
Logical
User Interface
Maintainability
Standards
Others